## Risk Register
PROJECT RISK REGISTER
Project Name: |  | Harcourt Street School Site | [32 empty] | RISK COMPLETE
CPM Name: |  | BB
CPM Firm: |  | NPS
Updated (dd/mm/yy) |  | 2008-06-23
Risk ID No | Educational / Building risk? | Risk Description | Risk Category | Risk Sub-category | Current Status | Likelihood (%) |  | CONSTRUCTION RISK SCORE |  | EDUCATIONAL RISK SCORE |  |  | Cost |  | Time |  | Ethos |  |  | Achievement |  | Reputation | COMBINED RANKING |  | Risk Owner | Mitigation Action 1 | Action Owner | Action Date | Mitigation Action 2 | Action Owner | Action Date | Mitigation Action 3 | Action Owner | Action Date | Comments | Category drop down menus per risk |  |  | Risks derived from distinctive academy project organisational structures | Risks derived from site factors and surrounding area | Risks derived from project delivery | High risks | Medium risks | Low risks
| Source |  |  |  | User Defined Column 1 |  |  | Cost Severity (1-5) | Time Severity (1-5) | Ethos Severity (1-5) | Achievement Severity (1-5) | Reputation Severity (1-5) | Importance Indicator | Risk Ranking | Importance Indicator | Risk Ranking | Importance Indicator | Risk Ranking | Importance Indicator | Risk Ranking | Importance Indicator | Risk Ranking
1 | Building | Risk of Planning permission being refused | Risks derived from site factors and surrounding area |  | Closed |  | 3 | [6 empty] | low |  | low | low | low | low | low | low | low | low | low | LA/ PB | Identify any final outstanding issues, ensure all relevant reports prepared | DS | [8 empty] | Site condition | Planning and land ownership | Surrounding area and neighbouring community | 0 | 1 | 0 | 0 | 0 | 1
2 | Building | Risk of EA requiring additional reports and potential surveys (delays and costs) | Risks derived from project delivery |  | Open |  | 4 | [6 empty] | high |  | high | high | high | high | high | high | high | high | high | LA/ PB | EA costs to be identified within consultant charge. | AM/CW | [8 empty] | Design & project costing | Procurement | Construction & operation | 0 | 0 | 1 | 1 | 0 | 0
3 | Building | Risk of EA requiring drainage works in excess of allowed Prov Sum | Risks derived from project delivery |  | Open |  | 4 | [6 empty] | high |  | medium | high | high | high | high | high | high | high | high | LA/ PB | Review outcome of EA recommendations. | AM/CW | [8 empty] | Design & project costing | Procurement | Construction & operation | 0 | 0 | 1 | 1 | 0 | 0
4 | Building | Risk of Planning conditions bringing delays/costs not allowed for | Risks derived from project delivery |  | Open |  | 3 | [6 empty] | medium | medium | medium | medium | medium | medium | medium | medium | medium | medium | medium | LA/ PB | Project Board informed and other work sustained to ensure continued momentum of project | DS | [8 empty] | Design & project costing | Procurement | Construction & operation | 0 | 0 | 1 | 0 | 1 | 0
5 | Building | Risk of Members recalling scheme to committee (delays) | Risks derived from project delivery |  | Closed |  | 3 | [6 empty] | low | medium | medium | medium | medium | medium | medium | medium | medium | medium | medium | LA/ PB | Brief Executive members at key stages and communication with ward members. | DS/AW | [8 empty] | Design & project costing | Procurement | Construction & operation | 0 | 0 | 1 | 0 | 1 | 0
6 | Building | Risk of client not approving scheme at 'Commit to Invest' stage | Risks derived from distinctive academy project organisational structures |  | Closed |  | 2 | [6 empty] | low |  | low | low | low | low | low | low | low | low | low | LA/ PB | Ensure continued LA and Member support | DS | [8 empty] | Sponsor-related | Building-process party related | Educational party related | 1 | 0 | 0 | 0 | 0 | 1
7 | Building | Risk of client funding not meeting actual costs |  |  | Open |  | 2 | [6 empty] | low |  | low | low | low | low | low | low | low | low | low | LA/ PB | Further discussions with DBS. | DS/AW | [11 empty] | 0 | 0 | 0 | 0 | 0 | 1
8 | Building | Risk of Members not approving CPO in line with programme | Risks derived from project delivery |  | Closed |  | 2 | [6 empty] | low |  | low | low | low | low | low | low | low | low | low | LA/ PB | Provide full briefing to executive members | DS | [8 empty] | Design & project costing | Procurement | Construction & operation | 0 | 0 | 1 | 0 | 0 | 1
9 | Building | Risk of CPO objections forcing delays |  |  | Open |  | 5 | 2 | 4 |  |  |  |  | medium |  | high | high | high | high | high | high | high | high | high | LA/ PB | Amend critical time schedule for two potential completion dates. | DS | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0
10 | Building | Risk of CPO not being confirmed |  |  | Open |  | 1 | [6 empty] | low | low | low | low | low | low | low | low | low | low | low | LA/ PB | Produce full CPO report. | JH / BB | [11 empty] | 0 | 0 | 0 | 0 | 0 | 1
11 | Building | Risk of CPO compensation being paid (i.e. in excess of cost plan allowance) | Risks derived from site factors and surrounding area |  | Open |  | 3 | [6 empty] | medium | medium | medium | medium | medium | medium | medium | medium | medium | medium | medium | LA/ PB | Highlight within potential expenditure costs. | DS | [8 empty] | Site condition | Planning and land ownership | Surrounding area and neighbouring community | 0 | 1 | 0 | 0 | 1 | 0
11A | Building | Risk of Village Green application forcing delays |  |  | Open |  | 3 | 2 | 2 |  |  |  |  | medium | medium | medium | medium | medium | medium | medium | medium | medium | medium | medium | LA/ PB | Mitigating action to be completed as project progresses | JH / BB
12 | Building | Risk of OJEU notice not attracting suitable contractors | Risks derived from site factors and surrounding area |  | Open |  | 2 | [6 empty] | low |  | low | low | low | low | low | low | low | low | low | LA/ PB | Mitigating action to be completed as project progresses | AM/CW | [8 empty] | Site condition | Planning and land ownership | Surrounding area and neighbouring community | 0 | 1 | 0 | 0 | 0 | 1
13 | Building | Risk of client's needs changing during design process (affecting further changes) | Risks derived from site factors and surrounding area |  | Open |  | 3 | [6 empty] | low |  | medium | [5 empty] | low |  | low | LA/ PB | Mitigating action to be completed as project progresses | AM/CW | [8 empty] | Site condition | Planning and land ownership | Surrounding area and neighbouring community | 0 | 1 | 0 | 0 | 0 | 1
14 | Building | Risk of design resources not being available to meet programme | Risks derived from project delivery |  | Open |  | 2 | [6 empty] | low | low | low | low | low | low | low | low | low | low | low | LA/ PB | Mitigating action to be completed as project progresses | AM/CW | [8 empty] | Design & project costing | Procurement | Construction & operation | 0 | 0 | 1 | 0 | 0 | 1
15 | Building | Risk of changes to procurement regulations affecting programme/process | Risks derived from site factors and surrounding area |  | Open |  | 1 | [6 empty] | low | low | low | low | low | low | low | low | low | low | low | LA/ PB | Design team to present to project board highlighting financial implications | AM/CW | [8 empty] | Site condition | Planning and land ownership | Surrounding area and neighbouring community | 0 | 1 | 0 | 0 | 0 | 1
16 | Building | Risk of design being affected by change in legislation or DCSF guidelines |  |  | Open |  | 3 | [6 empty] | medium | medium | medium | medium | medium | medium | medium | medium | medium | medium | medium | LA/ PB | Design team to present to project board highlighting financial implications | AM/CW | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0
17 | Building | Risk of revised elevation treatments bringing extra costs (planning condition?) |  |  | Open |  | 2 | [6 empty] | low | low | low | low | low | low | low | low | low | low | low | LA/ PB | awaiting planning conditionms | AM/CW | [11 empty] | 0 | 0 | 0 | 0 | 0 | 1
18 | Building | Risk of design/tender process exceeding programmed time | Risks derived from project delivery |  | Open |  | 2 | [6 empty] | low | low | low | low | low | low | low | low | low | low | low | LA/ PB | Mitigating action to be completed as project progresses | AM/CW | [8 empty] | Design & project costing | Procurement | Construction & operation | 0 | 0 | 1 | 0 | 0 | 1
19 | Building | Risk of developing designs exceeding Stage D cost plan | Risks derived from project delivery |  | Open |  | 2 | [6 empty] | low | low | low | low | low | low | low | low | low | low | low | LA/ PB | Present to DBS and project board | AM/CW | [8 empty] | Design & project costing | Procurement | Construction & operation | 0 | 0 | 1 | 0 | 0 | 1
20 | Building | Risk of tender price exceeding cost estimates due to local factors not foreseen | Risks derived from site factors and surrounding area |  | Open |  | 2 | [6 empty] | low | low | low | low | low | low | low | low | low | low | low | LA/ PB | Present to DBS and project board | AM/CW | [8 empty] | Site condition | Planning and land ownership | Surrounding area and neighbouring community | 0 | 1 | 0 | 0 | 0 | 1
21 | Building | Risk of disturbance to local residents during piling works. |  |  | Open |  | 2 | [6 empty] | low | low | low | low | low | low | low | low | low | low | low | LA/ PB | Mitigating action to be completed as project progresses | AM/CW/AB
21A | Building | Risk of disruption of construction process | Risks derived from project delivery |  | Open |  | 3 | [6 empty] | medium | medium | medium | medium | medium | medium | medium | medium | medium | medium | medium | LA/ PB | Mitigating action to be completed as project progresses | AM/CW | [8 empty] | Design & project costing | Procurement | Construction & operation | 0 | 0 | 1 | 0 | 1 | 0
22 | Building | Risk of cost inflation exceeding that estimated | Risks derived from distinctive academy project organisational structures |  | Open |  | 2 | [6 empty] | medium |  | low | [5 empty] | low |  | low | LA/ PB | Design team to present to project board highlighting financial implications | AM/CW | [8 empty] | Sponsor-related | Building-process party related | Educational party related | 1 | 0 | 0 | 0 | 0 | 1
23 | Building | Risk of ground conditions not conforming to reported expectations | Risks derived from site factors and surrounding area |  | Open |  | 2 | [6 empty] | low |  | low | [5 empty] | low |  | low | LA/ PB | identify required actions in consultation with specialist advice | AM/CW | [8 empty] | Site condition | Planning and land ownership | Surrounding area and neighbouring community | 0 | 1 | 0 | 0 | 0 | 1
24 | Building | Risk of drainage connections not being possible where anticipated | Risks derived from distinctive academy project organisational structures |  | Open |  | 2 | [6 empty] | low | low | low | low | low | low | low | low | low | low | low | LA/ PB | Design team to present to project board highlighting financial implications | AM/CW | [8 empty] | Sponsor-related | Building-process party related | Educational party related | 1 | 0 | 0 | 0 | 0 | 1
25 | Building | Risk of Service connections costs exceeding provisional sums | Risks derived from site factors and surrounding area |  | Open |  | 2 | [6 empty] | low | low | low | low | low | low | low | low | low | low | low | LA/ PB | Design team to present to project board highlighting financial implications | AM/CW | [8 empty] | Site condition | Planning and land ownership | Surrounding area and neighbouring community | 0 | 1 | 0 | 0 | 0 | 1
26 | Building | Risk of developing designs not achieving Part L/SBEM | Risks derived from site factors and surrounding area |  | Open |  | 2 | [6 empty] | medium | low | low | low | low | low | low | low | low | low | low | LA/ PB | Mitigating action to be completed as project progresses | AM/CW | [8 empty] | Site condition | Planning and land ownership | Surrounding area and neighbouring community | 0 | 1 | 0 | 0 | 0 | 1
27 | Building | Risk of contractor going into liquidation during construction phase | Risks derived from distinctive academy project organisational structures |  | Open |  | 1 | [6 empty] | low | low | low | low | low | low | low | low | low | low | low | LA/ PB | Select contractor with due diligence checks | AM/CW | [8 empty] | Sponsor-related | Building-process party related | Educational party related | 1 | 0 | 0 | 0 | 0 | 1
28 | Building | Risk of delays to construction due to unforeseen weather conditions | Risks derived from site factors and surrounding area |  | Open |  | 2 | [6 empty] | low | low | medium | low | low | low | low | low | low | low | low | LA/ PB | Contractor to programme the works with reasonable allowances for inclement weather | AM/CW | [8 empty] | Site condition | Planning and land ownership | Surrounding area and neighbouring community | 0 | 1 | 0 | 0 | 0 | 1
29 | Building | Risk of contractors failing to meet the programme | Risks derived from site factors and surrounding area |  | Open |  | 2 | [6 empty] | low | low | low | low | low | low | low | low | low | low | low | LA/ PB | Systems in place to ensure tight performance management | AM/CW | [8 empty] | Site condition | Planning and land ownership | Surrounding area and neighbouring community | 0 | 1 | 0 | 0 | 0 | 1
30 |  | Risk of security problems during construction causing costs/delay | Risks derived from distinctive academy project organisational structures |  | Open |  | 2 | [6 empty] | medium |  | low | low | low | low | low | low | low | low | low | LA/ PB | Contractor to provide 24 hour security and erect permanent fence early in construction | AM/CW | [8 empty] | Sponsor-related | Building-process party related | Educational party related | 1 | 0 | 0 | 0 | 0 | 1
31 | Building | Key staff leave because of delays in scheme | [11 empty] | low |  | low | [5 empty] | medium |  | low | LA/ PB | Develop staff communication plan | DS | [11 empty] | 0 | 0 | 0 | 0 | 0 | 1
32 | Educational | DCF is utilised for other schemes on existing site | Risks derived from project delivery | [10 empty] | medium |  | low | [5 empty] | low |  | low | LA/ PB | Restrict expenditure on key health and safety requirements | DS | [8 empty] | Design & project costing | Procurement | Construction & operation | 0 | 0 | 1 | 0 | 0 | 1
33 | Educational | School Adjudicator rejects request for deferment of school closure | Risks derived from site factors and surrounding area |  | Closed | [8 empty] | low |  | low | [5 empty] | high |  | medium | LA/ PB | Identify acting up arrangements | DS | [8 empty] | Site condition | Planning and land ownership | Surrounding area and neighbouring community | 0 | 1 | 0 | 0 | 1 | 0
34 | Educational | Parents lose confidence in new build and pupils are sent to other schools | Risks derived from project delivery | [10 empty] | low |  | low | [5 empty] | high |  | medium | LA/ PB | Communication plan for parents to be developed | DS | [8 empty] | Design & project costing | Procurement | Construction & operation | 0 | 0 | 1 | 0 | 1 | 0
35 | Educational | Conditons in existing school buildings continue to deteriorate | Risks derived from distinctive academy project organisational structures | [10 empty] | medium |  | low | [5 empty] | low |  | low | LA/ PB | Tightly monitor problems and identify funding to ammeliorate any problems | DS | [8 empty] | Sponsor-related | Building-process party related | Educational party related | 1 | 0 | 0 | 0 | 0 | 1
36 | Educational | Standards at schools fall because of uncertainly if scheme | Risks derived from project delivery | [10 empty] | low |  | low | [5 empty] | medium |  | medium | LA/ PB | SIA and HTs continue to implement programmes to secure the maintanance of high standards | DS | [8 empty] | Design & project costing | Procurement | Construction & operation | 0 | 0 | 1 | 0 | 1 | 0
| Educational |  | Risks derived from site factors and surrounding area | [32 empty] | Site condition | Planning and land ownership | Surrounding area and neighbouring community | 0 | 1 | 0 | 0 | 0 | 0
|  |  | Risks derived from project delivery | [9 empty] | 0 | [22 empty] | Design & project costing | Procurement | Construction & operation | 0 | 0 | 1 | 0 | 0 | 0
|  |  | Risks derived from distinctive academy project organisational structures | [9 empty] | 0 | [22 empty] | Sponsor-related | Building-process party related | Educational party related | 1 | 0 | 0 | 0 | 0 | 0
|  |  | Risks derived from distinctive academy project organisational structures | [9 empty] | 0 | [22 empty] | Sponsor-related | Building-process party related | Educational party related | 1 | 0 | 0 | 0 | 0 | 0
|  |  | Risks derived from project delivery | [9 empty] | 0 | [22 empty] | Design & project costing | Procurement | Construction & operation | 0 | 0 | 1 | 0 | 0 | 0
|  |  | Risks derived from site factors and surrounding area | [9 empty] | 0 | [22 empty] | Site condition | Planning and land ownership | Surrounding area and neighbouring community | 0 | 1 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | [5 empty] | 0 | Nil | 0 | Nil | 0 | Nil | 0 | Nil | 0 | Nil | 0 | Nil | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | [5 empty] | 0 | Nil | 0 | Nil | 0 | Nil | 0 | Nil | 0 | Nil | 0 | Nil | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | [5 empty] | 0 | Nil | 0 | Nil | 0 | Nil | 0 | Nil | 0 | Nil | 0 | Nil | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | [5 empty] | 0 | Nil | 0 | Nil | 0 | Nil | 0 | Nil | 0 | Nil | 0 | Nil | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | [5 empty] | 0 | Nil | 0 | Nil | 0 | Nil | 0 | Nil | 0 | Nil | 0 | Nil | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | [5 empty] | 0 | Nil | 0 | Nil | 0 | Nil | 0 | Nil | 0 | Nil | 0 | Nil | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | [5 empty] | 0 | Nil | 0 | Nil | 0 | Nil | 0 | Nil | 0 | Nil | 0 | Nil | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | [5 empty] | 0 | Nil | 0 | Nil | 0 | Nil | 0 | Nil | 0 | Nil | 0 | Nil | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | [5 empty] | 0 | Nil | 0 | Nil | 0 | Nil | 0 | Nil | 0 | Nil | 0 | Nil | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | Category 1 | Category 2 | Category 3 | High | Medium | Low
[5 empty] | Open | [33 empty] | 8 | 14 | 14 | 3 | 8 | 25
| Educational |  |  |  | Closed | [33 empty] | 22.22% | 50% | 82.35%
Building
Educational / Building

## Categories (hidden)
CATEGORIES
Category | Sub-cetagory 1 | Sub-category 2 | Sub-category 3
Risks derived from distinctive academy project organisational structures | Sponsor-related | Building-process party related | Educational party related
Risks derived from site factors and surrounding area | Site condition | Planning and land ownership | Surrounding area and neighbouring community
Risks derived from project delivery | Design & project costing | Procurement | Construction & operation