## Project Plan
Activity | Category | Date | Status | Comments
Get a Book Idea | Preparation
Discover your Author Personality | Preparation |  |  | See Robin Colucci's book
Set goals and timelines | Preparation
Work idea to Develop Book Concept | Preparation |  |  | See Robin Colucci's book
Why are your writing? Personal & business goals related to book. | Preparation
What is the book about? What is the central idea? The main take-away? | Preparation |  |  | A very short statement that summarizes the book subject at its core. This should be no longer than a sentence or two. Imagine what a reader would tell their friend if they were asked, “That book you’re reading, what’s it about?”
Who will read it? Traits of your audience. How many potential readers? | Preparation
Why they will read it? The key benefit of reading the book? | Preparation |  |  | What is the essential point(s) you are making for your audience? What are the main points you want the audience to take away from your book? What, specifically, will your audience get by reading your book? How does your book help your audience achieve their goals?
What difference do you want to make in the world? | Preparation
Test Book Concept - look at the market | Preparation |  |  | Can you identify 5-10 books that your book will be similar to? Which categories do they sit in? Where do they fit in the ecosystem?
What kind of book it is? What's the genre? | Preparation
How does your book compare to other similar books in the market? | Preparation
What makes yours unique? | Preparation |  |  | Why are you the right person for this book? Lots of people write about the same topics – but your experiences make your book original. It's your take on the subject. You have to trust yourself and lean into what makes you YOU. Brainstorm aspects of your life that might be more interesting to other people than it is to you. What's interesting about your background that will help you stand out?
Why are you the best/only person to write it? | Preparation
What is missing in the market and is needed that your book brings? | Preparation
Finalize your Bestseller Blueprint. How will you structure it? | Preparation |  |  | See Robin Colucci's book
Outline the book | Preparation
Define the ideas you will cover, begin to set order/flow | Preparation
Define the key points under the main ideas within the outline | Preparation
Identify research needs and conduct research | Research
Build Research Database | Research
Read/review research materials | Research
Write Research Notes and add relevant quotes to Research Database | Research
Write the Book: number of words you plan to write per deadline | Writing |  |  | Assume 500 words/hours, 5,000 words every two weeks
65,000 words | Writing
Write Introduction/Preface, About the Author, and Acknowledgments | Writing
Write glossary, resources, appendices, etc. as needed | Writing
Verify all sources, citations, bibliography, footnotes, etc. | Writing
Decide on the Book Title | Writing
Self Edit | Editing |  |  | Leave the manuscript for at least a week. This first round of editing is more about structure, missing sections, and big issues than it is about grammar and sentence structure.
Update draft after self-edit round | Editing
Send to friends, peers, cooleagues, other writers for review & feedback | Review
Incorporate the feedback you agree with into your revision | Review
Send manuscript to a paid, professional structural ( developmental) editor | Editing |  |  | A structural or developmental editor will work with you at a high level to shape the book into a coherent flow. They will read your manuscript and then provide a report about content organization, missing sections, tone and voice, as well as suggestions for improvement.
Incorporate the feedback you agree with into your revision | Editing
Send manuscript to a paid, professional copy editor | Editing |  |  | A copy editor or line editor focuses on improving sentences, grammar, and style, as well as suggesting other ways of rephrasing ideas. They may also provide comments on anything else they pick up. Non-fiction books often use particular styles, for example, chapter headings, sub-headings, action points, bullet points, call-outs and examples, so these may be checked too. The copy editor will usually use Track Changes on MS Word. This is the classic 'red pen' edit where you can expect a lot of changes.
Editor completes Round 1 of edits (longest edit) | Editing
Round 1 edits returned to author | Editing
Author reviews and sends to editor for Round 2 (1/2 the time as Round 1) | Editing
Round 2, editor reads again and returns to author | Editing
Author reviews and sends to editor for Round 3 (1/2 the time as Round 2) | Editing
Editor completes Round 3 and returns to editor for Final Approval | Editing
Author approves and returns to editor for final sweep and formatting | Editing
Send final manuscript to a professional proofreader | Editing |  |  | A proofreader checks the manuscript line by line in the stage before publication. You should have made any changes based on previous editing rounds, and then the proofreader is the final check. They should not find anything significant at this stage but will note typos or incorrect use of words, inconsistencies in formatting, and other specific details.
Author reviews proofread manuscript | Editing
Manuscript ready for outside eyes (agent, layout/design, book packager) | Editing
Layout | Design |  |  | Hire a book designer/professional formatter
Cover Design | Design
Marketing | Marketing
Request blurb quotes | Marketing
Pricing | Marketing
Write Book Sales Description | Marketing
Create Book Page | Marketing
Update Website | Marketing
Add affiliate links | Marketing
Press page or media kit | Marketing
Paid Advertising | Marketing
Build E-Mail List | Marketing |  |  | Add the sign-up to the back of your books, website. Include a Call to Action in your book for the reader to sign up for an extra ebook or updates Include links in your book for extra bonuses.
Content Marketing | Marketing |  |  | Blog posts
Social Media Marketing | Marketing
Sales | Sales
Sell directly from your website | Sales

## Writing Tracker
When I wrote my first book, I created a simple spreadsheet that had all the chapters listed with a short description and then cells to keep track of the word count. As I wrote more each week, little by little I saw my progress adding up to a full-length book.
Deadline | Word Count | Actual Count | Delta | Chapter | Chapter Description | Comments
| 5000 |  | 5000
| 5000 |  | 5000
| 5000 |  | 5000
| 5000 |  | 5000
| 5000 |  | 5000
| 5000 |  | 5000
| 5000 |  | 5000
| 5000 |  | 5000
| 5000 |  | 5000
| 5000 |  | 5000
| 5000 |  | 5000
| 5000 |  | 5000
Total | 60000 | 0 | 60000