Women and Girls for Change

Narrative Annual Reporting Format

| General information |  |
| --- | --- |
| Programme | Women & Girls for Change |
| Name of Reporting organization | Support Trust for Africa Development (STAD) |
| Name of Partner organization in South Sudan | Equatoria Women Organisation (EW0) |
| Location(s) of implementation in South Sudan | Torit |

- CONTEXT

Context Describe the main changes in the context and how they affected the project implementation. Focus more on the local level, but include the national level where important.

The project implementation in Torit went smoothly (has not been so much affected) though there were main changes in the project context as a result of reductions in budget lines, number of planned participants and rescheduling some of the planned activities to 2018 due to budget constraints and late start of the actual work.

- RESULTS

| Per Pathway: |  |
| --- | --- |
| Pathway 1: Women and Girls are more resilient and better protected |  |
| Short term outcome realised | Participants were trained & acquired knowledge & skills on gender &human right concepts in the project area. The awareness raising and dialogue activities on human rights, UNSCR 1325 etc. were conducted aimed at community behavioural or negative mindset changes towards women leadership, domestic violence, GBV, women participation in decision making & in leadership positions etc. |
| Progress towards medium term outcomes | The debates and discussion on issues of peaceful co-existence in a Community & women’s vital roles in a society etc. have started evolving in and among community members, women groups and the youth. However, these debates and dialogues etc. still need to be reinforced with programs on education of women leadership, chiefdom ship, judges, rule of the law enforcement mechanisms and police and prison, male role models as agents of change for women to be better protected. |
| Pathway 2: An enabling environment exists for the promotion of gender equality |  |
| Short term outcome realised | Awareness activities conducted, people acquired ideas and knowledge and information about their rights and have started putting the idea into practice |
| Progress towards medium term outcomes | Women have started taking up leadership positions in both government and NGOs and have started raising complaints about their rights violation and some men understood some of the negative cultural and traditional norms against the women. Some men have started allowing women to leadership positions, respect for women rights to participate equally in public affairs despite the deeply rroted cultural paratracheal norms |
| Pathway 3: Women and girls are meaningfully engaged in local decision making related to conflict prevention and resolution, peace building, relief and recovery. |  |
| Short term outcome realised | Conflict transformation and peace building activities conducted, community equipped with peace building knowledge and shared experiences and have started managing social conflicts within their local society (ies) |
| Progress towards medium term outcomes | Women are now aware about their rights and have started developing interest in leadership position and have started assuming some leadership positions in the community and are now actively advocating for political and community decision positions |
| Cross-cutting issues What have you done to ensure implementation/integration of the following. Describe in each location what kind of approach have you used, how the activities have been adapted, if you have encountered resistance to each of the crosscutting approaches, etc. |  |
| Resilience strengthening | Though women are now aware on the concept of gender equality, human & women rights under the WG4C Alliance interventions. they there are not much mechanism to support strengthen and protect in the community to be treated to some extent as equals or with respect and dignity |
| Capacity building of civil society | The capacity building of the civil society adds value to the capacity needed for the Alliance project implementation and will help improve performance and attainment of project goal |
| Gender transformative approach | This is a great approach because it puts gender at an equal footing as it addresses all aspect of life: Gender mainstreaming in program, decision, leadership and other community related social programs, hence reducing discrimination and gender based violence |
| Girls and Women Empowerment | This is one of the main activity conducted by EWO under WG4C Alliance to empower women in social, economic, cultural and political areas in a male dominant community environment. Focusing on women and girls’ empowerment will limit very serious gender discrimination that existed in the region, and hence contributing positively for poverty reduction/eradication and women emancipation in the community |
| Men and boys Engagement | The engagement of both men and boys in this project has great value added. Because its men and boys who still to some negative cultural practices denying women their based human rights. So taking them through the concept of gender and human rights help them to understand gender equality, human or women right which must be respected |
| Meaningful Youth participation | Though STAD/EW0 have not yet implemented the training on youth as agents of change, it is a very vital element if the WG4CA project. The youth are one of the key member of society. Activities of the women girls for change alliance because such influences their behaviour and attitude and train them as agents of change or champion of changes through joint peace building activities like games and sports |

- UNINTENDED RESULTS and UNFORSEEN CONSEQUENCES

Unintended Results Describe if there were any unintended results or unforeseen consequences due to the project. Unintended results are positive changes (outcomes) that happened as a direct consequence of the project implementation, but they were not planned for. Remember that there could also be negative consequences of the project.

The kick off planned activities is very important for this project as it set the ground for the project implementation using a unified approach. Second is the project launching and participation in the 16th day of activism in December- very important for the project though were not planned and had no budget lines.

- COLLABORATION

| Please answer the following questions: - How do you asses the collaboration of the alliance that took place? Reflect on frequency, intensity and quality of the collaboration. - What are your two suggestions for taking collaboration forward? |  |
| --- | --- |
| - Assessment of the collaboration | - Frequency: positive for Alliance meeting in Netherlands. Poor for field meetings (irregular) - Intensity: positive has improved. STAD was able to get some support, advice and documents from other partners. - Quality: Poor and confusing. Too many changes in formats of reporting .This could be due to changes in Alliance coordinator and finance staff? |
| - Suggestions for improvement | - Regular field meetings to assess and monitor project progress to identify gaps and fill them before hand - More practical/physical interaction with the project implementing team and access to the target beneficiaries to directly assess work progress |

- CAPACITY BUIDLING

| Please summarise the progresses made on capacity building |  |
| --- | --- |
| Technical capacities | EW0 staff capacity building exercise has just been conducted in February this year (2018). Lesson learnt shows that this should have been conducted earlier in 2017 as it contributions a lot of technical support on how to manage project and program activities implementation |
| Financial capacities | The capacity building training conducted adds value to the existing financial management of the organization and this capacity will help on the project financial management and finance of the organization because it enables best financial practice |
| Management capacities | The management has acquired more additional knowledge on the organizational management with regards to both financial and program management |
| Other capacities | The training involved some value-added components like logistic and procurement plus Asset management, all this are beneficial for the project management although much or more may be required in future |

- CHALLENGES

| Can you name 2 - 3 challenges in the implementation of the activities and if so, please describe how did you deal with these challenges? |  |
| --- | --- |
| Challenges at Implementation level (not context) | - Insecurity in the Country Affected project working negatively - High cost of goods and services in market affected project budget - Insecure and inaccessible roads |
| How did you handle these challenges? | - Involvement of the relevant government officials in the project enabled or solved insecurity related issues - Budget adjustment to meet the current cost of living - The use of flight helped solve the insecure road network |
| Do you expect these challenges to influence work in the future? | These challenges may in future affect the project implementation negatively if the insecurity situation and high costs of goods and material intensifies in South Sudan. More efforts needed to achieve peace so that people could return to relative normal life in the Country. Thus, creating room for easy and effective project implementation |

- SUPPORT

| Are there any capacity issues that need support to increase the quality of your implementation? Such as M&E, Finance, Alliance Building, or technical aspects such as Meaningful Youth Participation, Gender Transformative Approach, Girls Empowerment, Men and boys Engagement. Please explain what support you need on which specific issues and why you need this support. |  |
| --- | --- |
| M&E | Support needed on: M&E expert/ person (position) to be responsible in the follow up and documenting progress of the project in field. Because: For staff easy project management, M&E for monitoring and evaluation this project by the organization because we don’t have one, training manual for a joint project approach |
| Finance | Support needed on: Need for re-adjustment to fit the current cost of living. Need for more financial management training. Because: Budget adjustment for meet the current cost of living, more financial management financial and project management training for proper and efficient and project implementation |
| Alliance building | Support needed on: The need for strengthening the Alliance beyond the current consortium, strengthening the capacity of the Alliance partners of this consortium for further involvement. Because: To ensure that the concept of UNSCR 1325 is carried forward by strengthening of the Alliance partners capacities to understand beyond this project the concept of UNSCR 1325 and to incorporate it into their other organization program. |
| Meaningful Youth Participation | Support needed on: additional financial support is needed and the definition of the concept for easy and clear understanding by implementing partners in their respective approach Because: The concept not clear for the process of implementation |
| Girls Empowerment | Support needed on: Awareness program and education for girls and some income earning activities to support them become independent are needed Because: wider scope of understanding girls education will help reduce poverty among girls through income earning program (for non- school going or drop out or teen mothers group) |
| Men and boys Engagement | Support needed on: more boys and men to be involved in the gender and human right awareness intervention and games and sport activities Because: For equal participation and peaceful co-existence between men and women and also poverty eradication among women |
| Gender Transformative Approach | Support needed on: More gender transformative program needed Because: To help better understand the concept of gender equality and human and women rights to create basis of respect and inclusiveness or socialization through games and sports |
| Other Support | Support needed on: Need to back women empowerment program with an income generating activities to improve their livelihood EW0 staff capacity training was very good and beneficial for the staff involved in the project and therefore, call for another follow up of such training. Joint manual development for gender transformative approach, youth Agent for change and Girl empowerment Because: Acquired knowledge about gender and human right will improve women and girls’ livelihood and capacities for better resilience |

- ANY OTHER THOUGHTS

Any other issues you want to share?

Our local partner EWO is now based in Uganda, for security reason they moved from Yei, South Sudan. And our project Area is Torit. This results in increase of cost, since two offices and additional staff are needed for the field office and head office.